|  |
| --- |
| **Contract Addendum for consultancy to develop data analytical dashboards and engage on improving disclosure of infrastructure with government systems.**  Dr. Levi Kabagambe Bategeka  [levi.kabagambe@gmail.com](mailto:levi.kabagambe@gmail.com) |
| **Addendum to existing Contract**   1. This document is in reference to a contract agreement dated 24th March 2023 between Africa Freedom of Information Centre on behalf of CoST – Infrastructure Transparency Initiative, hereafter referred to as Client P.O Box 35643, Kampala, Uganda Telephone 0414 533 554 and Dr. Levi Kabagambe Bategeka hereafter referred to as “Consultant” 2. May it be known that the undersigned parties, for good consideration, do hereby agree to make the following changes and or additions that are outlined below? These additions shall be made valid as they are included in the original stated contract. 3. **Stated Contract for:** No-cost time extension for consultancy services as Consultant to develop data analytical dashboards and engage on improving disclosure of infrastructure with government systems.   **Clause to be amended**  This addendum seeks to amend section Seven (7), ofDeliverables, Reporting timeline and Supervision by extending the time frame of the work at no cost from 8th May to 30th June 2023   1. **Purpose of the Addendum**   This addendum is expected to provide additional time for the Consultant to provide professional and technical support in the development of the analytical dashboard, engagements with the OC4IDS help desk and compile the analytical report. The delayed delivery of the task is attributed to the following factors;   * Data inefficiencies with disclosed data that required two weeks of correspondences with PPDA and MoFPED * Reviewing the dashboard to secure approval from the OC4IDS, which took a week. * The scope of work was revised to further include additional indicators.   The time extension of one and half months will cover the time lost during the circumstances explained above and will be used to deliver the following tasks in the contract under section 5; 6 and 8;   * A total of four use cases * A designed and approved analytical platform * Disclosure performance report developed against agreed-upon indicators * Status report on the integration of the OC4IDS into the EGP * End of task report  1. No other terms or conditions of the above-mentioned contract shall be negated or changed as a result of this here stated addendum.   **Effective date of Addendum**   1. This addendum shall take effect on the date of signature by the parties.   **Dr. Levi Bategeka Kabagambe**   |  |  |  |  | | --- | --- | --- | --- | | Signature |  | Date | **5th May 2023** |   **Approved by: Gilbert Sendugwa (Executive Director AFIC)**  **Signature** Date **\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_5th May 2023**  **Witnessed by: Olive Kabatwairwe (Programme Coordinator CoST Uganda)**  Signature \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ Date: \_\_\_\_\_**5th May 2023 \_** |